## High-level Summary
Tech Platform Observability Initiative - High-Level Summary
METRIC PRIORITIES SUMMARY
Priority | Focus Areas | Response Time | Sprint Target
Critical | Error rates, latency, uptime, success rate | Immediate (<5 min) | Sprint 1-2
High | Tenant metrics, throughput, alerts, dependencies | Within 1 hour | Sprint 2-4
Medium | Usage, adoption, historical trends, Mission Control | 24-48 hours | Sprint 4-6
Low | Incident/change volume reporting | Weekly review | Backlog
TASK PRIORITIES SUMMARY
Priority | Task Categories | Examples | Sprint Target
Critical | Overview dashboard, Alerting, Instrumentation gaps, Synthetic monitoring | Create unified Tech Platform Overview dashboard | Sprint 1-2
High | Individual dashboards, Service enhancements, Label additions | Create individual service dashboards, Add histogram buckets, Add endpoint labels | Sprint 2-4
Medium | Mission Control integration | Onboard services to Mission Control, Configure health-metadata.json | Sprint 4-6
Low | — | — | Backlog
SERVICE READINESS STATUS
Service | Common Name | Language | Prometheus Status | Alerts/Runbooks | Recommended Action
service-config-manager | Config-Mgr | Python | ✅ Ready | ❌ Needs creation | Build dashboards → Create alerts
service-model-feedback | Model-Feedback | Python | ✅ Ready | ❌ Needs creation | Build dashboards → Create alerts
service-datascience-gateway | Gateway | Java | ⚠️ Partial (no histogram) | ❌ Needs creation | Dashboard exists - enhance
service-large-language-model | LLM | Python | ✅ Ready | ❌ Needs creation | Complete - minor enhancements
service-cmp-adapter | CMP-Adapter | Java | ❌ Missing | ❌ Missing | BLOCKED - investigate deployment
service-payroll-model | Payroll | Python | ⚠️ Partial (no status label) | ❌ Needs creation | Has endpoint labels ✅ but no HTTP status - can't calculate error rates

## Task-Service Matrix
Task | Priority | Metric(s) | Gateway | LLM | Config-Mgr | Model-Feedback | CMP-Adapter | Payroll | Jira
Build Grafana dashboards (error rates, latency, throughput, success rate) | Critical | 5xx Errors Trend, 4xx Errors Trend, Latency Metrics, Throughput Metrics, Success Rate | ✅ Complete | ✅ Complete | Required | Required | 🔴 BLOCKED | Required
Enhance existing dashboards (add missing panels) | High | App Dependency Health Checks, App (Custom) Errors Monitoring, Integration Metrics, Critical Business Metrics, Historical Trends | Required | Required | N/A | N/A | 🔴 BLOCKED | N/A
Create tenant-level dashboard views | High | Tenant Fairness Checks, Tenant: Error Rate, Tenant: Response Latency | ⚠️ TBD | ⚠️ TBD | ⚠️ TBD | ⚠️ TBD | 🔴 BLOCKED | ⚠️ TBD
Configure Arize Dashboard for Token/Cost Metrics | Medium | Usage Metrics, Adoption Metrics | N/A | Required | N/A | N/A | N/A | N/A | PS-721646
Add histogram buckets for accurate P95/P99 latency | Critical | HTTP Response Latency, Latency Metrics | Required | ✅ Complete | N/A | N/A | 🔴 BLOCKED | N/A
Add endpoint/uri labels to metrics | Critical | HTTP Response Latency, Latency Metrics | N/A | N/A | Required | Required | 🔴 BLOCKED | ✅ Has labels | PS-721616
Add http_status label to metrics | Critical | 5xx Errors Trend, 4xx Errors Trend, App Error Rate, Success Rate | ✅ Has label | ✅ Has label | ✅ Has label | ✅ Has label | 🔴 BLOCKED | 🔴 Required
Investigate tenant metrics approach (product_id not available) | High | Tenant Fairness Checks, Tenant: Error Rate, Tenant: Response Latency | ⚠️ Investigate | ⚠️ Investigate | ⚠️ Investigate | ⚠️ Investigate | 🔴 BLOCKED | ⚠️ Investigate | PS-721596
Investigate service-cmp-adapter Prometheus deployment | Critical | All metrics | N/A | N/A | N/A | N/A | 🔴 Critical | N/A
Create alert rules | High | Alerts Configured w/ Actionable SOPs, False Alarms (count), Alert Volume (count) | ✅ Exists | ⚠️ Partial | Required | Required | 🔴 BLOCKED | 🔴 BLOCKED
Write runbook/SOP documentation | High | Alerts Configured w/ Actionable SOPs, MTTA (mins), MTTM (mins) | ✅ Exists | ⚠️ Partial | Required | Required | 🔴 BLOCKED | 🔴 BLOCKED
Configure PagerDuty integration | High | Alerts Integration w/ PD, MTTA (mins), MTTM (mins), Incident Volume (count) | Required | Required | Required | Required | 🔴 BLOCKED | Required
Configure ui-metadata.json for Mission Control | Medium | Mission Control: Service View Onboarded | Required | Required | Required | Required | Required | Required
Configure health-metadata.json | Medium | Mission Control: Critical Health Metrics, Mission Control: Dependencies Health Embedded, Mission Control: Cloud Infra Health Embedded | Required | Required | Required | Required | 🔴 BLOCKED | Required
Implement synthetic monitoring (internal - TBD) | Critical | Actual Uptime | Required | Required | Required | Required | Required | Required

## Layer-Metric Map
Layer | Layer Category | Metric | Metric Definition
Layer 3 | Application-Specific Metrics | 5xx Errors Trend | Service measures the 5xx errors trends to see anomalies.
Layer 3 | Application-Specific Metrics | 4xx Errors Trend | Service measures the 4xx errors trends to see anomalies.
Layer 3 | Application-Specific Metrics | HTTP Response Latency | Service monitors the response latency of your HTTP request traffic. It's a critical performance metric, directly impacting user experience and overall application responsiveness.
Layer 3 | Application-Specific Metrics | App Dependency Health Checks | Service performs the Application dependency health checks to ensure no upstream / downstream issues.
Layer 3 | Application-Specific Metrics | App (Custom) Errors Monitoring | Service monitors custom (application specific) error checks to observe any anomalies which could cause business distrubtion.
Layer 3 | Application-Specific Metrics | App Error Rate | Service monitors the Application error rate within the defined threshold budget.
Layer 3 | Application-Specific Metrics | Mission Control: Service View Onboarded | Service is onboarded to Mission Control.
Layer 3 | Application-Specific Metrics | Mission Control: Critical Health Metrics | Service has integrated right set of health metrics to help detect issues promptly during incident triage.
Layer 3 | Application-Specific Metrics | Mission Control: Dependencies Health Embedded | Service has embedded all application shared dependencies within their service architecture e.g., AuthN, API Gateway etc.
Layer 3 | Application-Specific Metrics | Mission Control: Cloud Infra Health Embedded | Service has embedded all applicatin cloud dependencies within their service architecture e.g., ELB, ILB, DNS etc.
Layer 4 | Business Value and User Impact | Actual Uptime | Actual service availability (uptime) in production. This is based on combination of 2 key metrics: a) Synthetics: Service Availability b) VM node / Pod uptime availability
Layer 4 | Business Value and User Impact | Success Rate | Service monitors the success rate. This indicate the percentage of successful business transactions serviced (interactive and/or background processing).
Layer 4 | Business Value and User Impact | Integration Metrics | Service monitors the integration touch points primarily w.r.t upstream and downstream services. This helps gain insights if data is exchanged as per the defined contract.
Layer 4 | Business Value and User Impact | Usage Metrics | Service monitors usage metrics to understand how the system, application, and/or a given feature is being used by the customer. This help understand users behavior, interaction with the system etc. | .
Layer 4 | Business Value and User Impact | Throughput Metrics | Service measures the number of requests handled by the system per unit of time (e.g., requests per second).
Layer 4 | Business Value and User Impact | Latency Metrics | Service measures the time taken for requests to complete, usually tracked using percentiles (e.g., p95, p99) to capture slowest responses.
Layer 4 | Business Value and User Impact | Critical Business Metrics | Service measures all the business metrics which are critical to an business application to help maintain customer experience.
Layer 4 | Business Value and User Impact | Tenant Fairness Checks | Service measures the tenant fairness end to end. This ensures that each tenant gets fair access to resources and services, even when they are sharing the same infrastructure.
Layer 4 | Business Value and User Impact | Tenant: Error Rate | Service measures the tenant specific error rate.
Layer 4 | Business Value and User Impact | Tenant: Response Latency | Service measures tenant specific response latency. This would help in gaining insights on tenant specific issues (e.g. high latency due to noisy tenant in the system).
Layer 4 | Business Value and User Impact | Adoption Metrics | Service measure how well users integrate a product or feature into their regular usage, indicating the success of new releases or features. These metrics provide valuable insights into user behavior and help product teams understand if their efforts are meeting user needs and goals. | .
Layer 4 | Business Value and User Impact | Historical Trends | Service monitors Historical trends to spot long term issues, such as performance degradation, memory leak, resource overuse.
Layer 4 | Business Value and User Impact | Alerts Configured w/ Actionable SOPs | Service alerts have actionable SOPs to restore service and/or business functionality.
Layer 4 | Business Value and User Impact | Alerts Integration w/ PD | Service alerts are configured to UKG incident management system, Pager Duty, to prevent and resolve business-impacting incidents.
Layer 5 | Observability Outcomes | MTTA (mins) | Average time it takes from when an alert is triggered to when work begins on the issue. This metric is useful for tracking your team’s responsiveness and your alert system’s effectiveness. To calculate your MTTA, add up the time between alert and acknowledgement, then divide by the number of incidents. | .
Layer 5 | Observability Outcomes | MTTM (mins) | Average time it takes to resolve a system or product failure, from the time the problem occurs to when the system is fully operational again. This is a crucial metric for understanding how efficiently an organization can respond to and resolve incidents, ultimately impacting system reliability and user satisfaction. It is calculated by summing the total time taken to mitigate all incidents within a specific period and then dividing that total by the number of incidents during that period. | .
Layer 5 | Observability Outcomes | False Alarms (count) | Total count of alerts that indicates a problem or threat when, in reality, there is none.
Layer 5 | Observability Outcomes | Alert Volume (count) | The count of alerts generated in Pager Duty for a Service.
Layer 5 | Observability Outcomes | Incident Volume (count) | The number of incidents opened for a Service resulted in a swarm bridge.
Layer 5 | Observability Outcomes | Change Volume (count) | The number of changes related to emergency fixes and/or critical updates post a standard release.

## Layer-Metric-Task Map
LAYER-METRIC-TASK MAP (with Gateway Status)
Layer | Category | Metric | Priority | Task(s) to Complete | Gateway Status | Gateway Notes
Layer 3 | Application-Specific Metrics | 5xx Errors Trend | Critical | Build Grafana dashboards for Python services; Enhance Gateway dashboard | ✅ | Panel: "5xx Error Rate (Current)" + "Success & Error Rate Trend" + "5xx Error Rate by URI"
Layer 3 | Application-Specific Metrics | 4xx Errors Trend | Critical | Build Grafana dashboards for Python services; Enhance Gateway dashboard | ✅ | Panel: "4xx Error Rate (Current)" + "4xx Error Rate by URI"
Layer 3 | Application-Specific Metrics | HTTP Response Latency | Critical | Build Grafana dashboards for Python services; Add histogram buckets to Gateway; Add endpoint/uri label to Python services | ⚠️ | Has avg/max latency, P95 is ESTIMATED (avg*2) - no histogram buckets
Layer 3 | Application-Specific Metrics | App Dependency Health Checks | High | Build Grafana dashboards for Python services; Enhance Gateway dashboard | ⚠️ | Token validation metrics exist; no explicit dependency health panel
Layer 3 | Application-Specific Metrics | App (Custom) Errors Monitoring | Critical | Build Grafana dashboards for Python services | ⚠️ | Token validation errors tracked; no other custom error monitoring
Layer 3 | Application-Specific Metrics | App Error Rate | Critical | Build Grafana dashboards for Python services; Create alert rules for Python services; Add HTTP status label to service-payroll-model | ✅ | Panel: "Combined Error Rate (Current)" + HTTP status breakdown
Layer 3 | Application-Specific Metrics | Mission Control: Service View Onboarded | Medium | Onboard services to Mission Control | ❌ | Not yet onboarded to Mission Control
Layer 3 | Application-Specific Metrics | Mission Control: Critical Health Metrics | Medium | Configure health-metadata.json | ❌ | health-metadata.json not configured
Layer 3 | Application-Specific Metrics | Mission Control: Dependencies Health Embedded | Medium | Configure health-metadata.json | ❌ | health-metadata.json not configured
Layer 3 | Application-Specific Metrics | Mission Control: Cloud Infra Health Embedded | Medium | Configure health-metadata.json | ❌ | health-metadata.json not configured
Layer 4 | Business Value and User Impact | Actual Uptime | Critical | Implement synthetic availability tests | ❌ | No synthetic monitoring - requires Datadog setup
Layer 4 | Business Value and User Impact | Success Rate | Critical | Implement synthetic availability tests; Build Grafana dashboards for Python services | ✅ | Panel: "HTTP Success Rate (Current)"
Layer 4 | Business Value and User Impact | Integration Metrics | High | Build Grafana dashboards for Python services; Enhance Gateway dashboard | ⚠️ | Token validation shows auth integration; no other integration metrics
Layer 4 | Business Value and User Impact | Usage Metrics | Medium | Configure Arize Dashboard for Token/Cost Metrics; Enhance existing LLM service dashboard | N/A | Arize metrics are for LLM service, not Gateway
Layer 4 | Business Value and User Impact | Throughput Metrics | High | Build Grafana dashboards for Python services; Enhance Gateway dashboard | ✅ | Panel: "Current Request Rate (RPS)" + "Request Rate Over Time"
Layer 4 | Business Value and User Impact | Latency Metrics | Critical | Build Grafana dashboards for Python services; Add histogram buckets to Gateway; Add endpoint/uri label to Python services | ⚠️ | Avg latency ✅, P95/P99 estimated ⚠️ - needs histogram buckets
Layer 4 | Business Value and User Impact | Critical Business Metrics | High | Configure Arize Dashboard for Token/Cost Metrics; Enhance existing LLM service dashboard | ⚠️ | Token validation metrics present; no LLM-specific business metrics
Layer 4 | Business Value and User Impact | Tenant Fairness Checks | High | Create tenant-level dashboard views (requires tenant label investigation) | ❌ | product_id not available; substream_id available but usage TBD
Layer 4 | Business Value and User Impact | Tenant: Error Rate | High | Create tenant-level dashboard views (requires tenant label investigation) | ❌ | Error rates exist but no tenant-level breakdown
Layer 4 | Business Value and User Impact | Tenant: Response Latency | High | Create tenant-level dashboard views (requires tenant label investigation) | ❌ | Latency exists but no tenant-level breakdown
Layer 4 | Business Value and User Impact | Adoption Metrics | Medium | Enhance existing LLM service dashboard | N/A | Adoption metrics are for LLM service features
Layer 4 | Business Value and User Impact | Historical Trends | Medium | Build Grafana dashboards for Python services; Enhance Gateway dashboard | ✅ | Multiple timeseries panels show historical trends
Layer 4 | Business Value and User Impact | Alerts Configured w/ Actionable SOPs | High | Create alert rules for Python services; Write runbook/SOP documentation | ❌ | Alerts need creation per High-level Summary
Layer 4 | Business Value and User Impact | Alerts Integration w/ PD | High | Configure PagerDuty integration | ❌ | PagerDuty integration pending
Layer 5 | Observability Outcomes | MTTA (mins) | High | Configure PagerDuty integration; Create alert rules for Python services | ❌ | Requires alerts + PagerDuty integration
Layer 5 | Observability Outcomes | MTTM (mins) | High | Configure PagerDuty integration; Write runbook/SOP documentation | ❌ | Requires alerts + runbooks
Layer 5 | Observability Outcomes | False Alarms (count) | Low | Create alert rules for Python services (tune thresholds) | ❌ | No alerts configured yet
Layer 5 | Observability Outcomes | Alert Volume (count) | Low | Create alert rules for Python services; Configure PagerDuty integration | ❌ | No alerts configured yet
Layer 5 | Observability Outcomes | Incident Volume (count) | Low | Configure PagerDuty integration | ❌ | Requires PagerDuty integration
Layer 5 | Observability Outcomes | Change Volume (count) | Low | N/A - tracked via change management process | N/A | Tracked externally via change management
GATEWAY STATUS SUMMARY
✅ Implemented: | 6
⚠️ Partial: | 6
❌ Not Implemented: | 15
N/A: | 3
PRIORITY LEGEND
Critical | Error rates, latency, uptime, success rate - Immediate (<5 min)
High | Tenant metrics, throughput, alerts, dependencies - Within 1 hour
Medium | Usage, adoption, historical trends, Mission Control - 24-48 hours
Low | Incident/change volume reporting - Weekly review
STATUS LEGEND
✅ = Fully implemented in Grafana dashboard
⚠️ = Partially implemented (has panels but with limitations)
❌ = Not implemented / requires work
N/A = Not applicable to this service

## Metric-Task Requirements
METRIC-TO-TASK REQUIREMENTS MAP
Tasks required to satisfy each metric by service
Layer | Category | Metric | Priority | Gateway | LLM | Config-Mgr | Model-Feedback | CMP-Adapter | Payroll
Layer 3 | Application-Specific Metrics | 5xx Errors Trend | Critical | ✅ Complete | ✅ Complete | Build Grafana dashboard with 5xx error panels | Build Grafana dashboard with 5xx error panels | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status label to metrics first
Layer 3 | Application-Specific Metrics | 4xx Errors Trend | Critical | ✅ Complete | ✅ Complete | Build Grafana dashboard with 4xx error panels | Build Grafana dashboard with 4xx error panels | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status label to metrics first
Layer 3 | Application-Specific Metrics | HTTP Response Latency | Critical | Add histogram buckets for accurate P95/P99 | ✅ Complete (has histogram buckets) | 1) Add endpoint labels to latency metrics; 2) Build dashboard | 1) Add endpoint labels to latency metrics; 2) Build dashboard | 🔴 BLOCKED: Investigate Prometheus deployment first | Build Grafana dashboard (has endpoint labels)
Layer 3 | Application-Specific Metrics | App Dependency Health Checks | High | Add dependency health check panels (beyond token validation) | Add dependency health check panels | Implement dependency health checks + dashboard | Implement dependency health checks + dashboard | 🔴 BLOCKED: Investigate Prometheus deployment first | Implement dependency health checks + dashboard
Layer 3 | Application-Specific Metrics | App (Custom) Errors Monitoring | Critical | Add custom error monitoring beyond HTTP status | Add custom error monitoring beyond HTTP status | Implement custom error metrics + dashboard | Implement custom error metrics + dashboard | 🔴 BLOCKED: Investigate Prometheus deployment first | Implement custom error metrics + dashboard
Layer 3 | Application-Specific Metrics | App Error Rate | Critical | ✅ Complete | ✅ Complete | Build Grafana dashboard with error rate panels | Build Grafana dashboard with error rate panels | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status label first
Layer 3 | Application-Specific Metrics | Mission Control: Service View Onboarded | Medium | Configure ui-metadata.json for Mission Control | Configure ui-metadata.json for Mission Control | Configure ui-metadata.json for Mission Control | Configure ui-metadata.json for Mission Control | Configure ui-metadata.json for Mission Control | Configure ui-metadata.json for Mission Control
Layer 3 | Application-Specific Metrics | Mission Control: Critical Health Metrics | Medium | Configure health-metadata.json with critical metrics | Configure health-metadata.json with critical metrics | Configure health-metadata.json with critical metrics | Configure health-metadata.json with critical metrics | 🔴 BLOCKED: Investigate Prometheus deployment first | Configure health-metadata.json with critical metrics
Layer 3 | Application-Specific Metrics | Mission Control: Dependencies Health Embedded | Medium | Add dependency health to health-metadata.json | Add dependency health to health-metadata.json | Add dependency health to health-metadata.json | Add dependency health to health-metadata.json | 🔴 BLOCKED: Investigate Prometheus deployment first | Add dependency health to health-metadata.json
Layer 3 | Application-Specific Metrics | Mission Control: Cloud Infra Health Embedded | Medium | Add cloud infra health to health-metadata.json | Add cloud infra health to health-metadata.json | Add cloud infra health to health-metadata.json | Add cloud infra health to health-metadata.json | 🔴 BLOCKED: Investigate Prometheus deployment first | Add cloud infra health to health-metadata.json
Layer 4 | Business Value and User Impact | Actual Uptime | Critical | Implement synthetic monitoring (internal - TBD) | Implement synthetic monitoring (internal - TBD) | Implement synthetic monitoring (internal - TBD) | Implement synthetic monitoring (internal - TBD) | Implement synthetic monitoring (internal - TBD) | Implement synthetic monitoring (internal - TBD)
Layer 4 | Business Value and User Impact | Success Rate | Critical | ✅ Complete | ✅ Complete | Build Grafana dashboard with success rate panel | Build Grafana dashboard with success rate panel | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status label first
Layer 4 | Business Value and User Impact | Integration Metrics | High | Add integration health panels beyond token validation | Add integration health panels | Implement integration metrics + dashboard | Implement integration metrics + dashboard | 🔴 BLOCKED: Investigate Prometheus deployment first | Implement integration metrics + dashboard
Layer 4 | Business Value and User Impact | Usage Metrics | Medium | N/A - LLM-specific metric | ✅ Complete (token count, avg tokens per call) | N/A - LLM-specific metric | N/A - LLM-specific metric | N/A - LLM-specific metric | N/A - LLM-specific metric
Layer 4 | Business Value and User Impact | Throughput Metrics | High | ✅ Complete | ✅ Complete | Build Grafana dashboard with RPS panels | Build Grafana dashboard with RPS panels | 🔴 BLOCKED: Investigate Prometheus deployment first | Build Grafana dashboard with RPS panels
Layer 4 | Business Value and User Impact | Latency Metrics | Critical | Add histogram buckets for accurate percentiles | ✅ Complete (P50, P90, P95, P99) | 1) Add endpoint labels; 2) Build dashboard with latency panels | 1) Add endpoint labels; 2) Build dashboard with latency panels | 🔴 BLOCKED: Investigate Prometheus deployment first | Build Grafana dashboard with latency panels
Layer 4 | Business Value and User Impact | Critical Business Metrics | High | Define and implement gateway-specific business metrics | ✅ Complete (token metrics) | N/A - service-specific | N/A - service-specific | N/A - service-specific | N/A - service-specific
Layer 4 | Business Value and User Impact | Tenant Fairness Checks | High | ⚠️ Investigate: product_id not available; substream_id usage TBD | ⚠️ product_id not available; investigate substream_id | ⚠️ product_id not available; substream_id available, usage TBD | ⚠️ product_id not available; substream_id available, usage TBD | 🔴 BLOCKED: Investigate Prometheus deployment first | ⚠️ product_id not available; substream_id available, usage TBD
Layer 4 | Business Value and User Impact | Tenant: Error Rate | High | ⚠️ Investigate: product_id not available; substream_id usage TBD | ⚠️ product_id not available; investigate substream_id | ⚠️ product_id not available; substream_id available, usage TBD | ⚠️ product_id not available; substream_id available, usage TBD | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: http_status label needed; product_id not available
Layer 4 | Business Value and User Impact | Tenant: Response Latency | High | ⚠️ Investigate: product_id not available; substream_id usage TBD | ⚠️ product_id not available; investigate substream_id | ⚠️ product_id not available; substream_id available, usage TBD | ⚠️ product_id not available; substream_id available, usage TBD | 🔴 BLOCKED: Investigate Prometheus deployment first | ⚠️ product_id not available; substream_id available, usage TBD
Layer 4 | Business Value and User Impact | Adoption Metrics | Medium | N/A - LLM-specific metric | ✅ Complete (endpoint distribution) | N/A - LLM-specific metric | N/A - LLM-specific metric | N/A - LLM-specific metric | N/A - LLM-specific metric
Layer 4 | Business Value and User Impact | Historical Trends | Medium | ✅ Complete | ✅ Complete | Build Grafana dashboard with timeseries panels | Build Grafana dashboard with timeseries panels | 🔴 BLOCKED: Investigate Prometheus deployment first | Build Grafana dashboard with timeseries panels
Layer 4 | Business Value and User Impact | Alerts Configured w/ Actionable SOPs | High | Create alert rules; write runbook documentation | Complete alert rules; write runbook documentation (panels exist) | Create alert rules; write runbook documentation | Create alert rules; write runbook documentation | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status label first; then create alerts
Layer 4 | Business Value and User Impact | Alerts Integration w/ PD | High | Configure PagerDuty integration for alerts | Configure PagerDuty integration for alerts | Configure PagerDuty integration for alerts | Configure PagerDuty integration for alerts | 🔴 BLOCKED: Investigate Prometheus deployment first | Configure PagerDuty integration for alerts
Layer 5 | Observability Outcomes | MTTA (mins) | High | Requires: Alert rules + PagerDuty integration | Requires: PagerDuty integration (alert panels exist) | Requires: Alert rules + PagerDuty integration | Requires: Alert rules + PagerDuty integration | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status first; then alerts + PD
Layer 5 | Observability Outcomes | MTTM (mins) | High | Requires: Alert rules + runbooks + PagerDuty | Requires: Runbooks + PagerDuty integration | Requires: Alert rules + runbooks + PagerDuty | Requires: Alert rules + runbooks + PagerDuty | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status first; then alerts + runbooks
Layer 5 | Observability Outcomes | False Alarms (count) | Low | Requires: Alert rules (then tune thresholds) | Requires: PagerDuty integration (then tune thresholds) | Requires: Alert rules (then tune thresholds) | Requires: Alert rules (then tune thresholds) | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status first; then alerts
Layer 5 | Observability Outcomes | Alert Volume (count) | Low | Requires: Alert rules + PagerDuty integration | Requires: PagerDuty integration | Requires: Alert rules + PagerDuty integration | Requires: Alert rules + PagerDuty integration | 🔴 BLOCKED: Investigate Prometheus deployment first | 🔴 BLOCKED: Add http_status first; then alerts + PD
Layer 5 | Observability Outcomes | Incident Volume (count) | Low | Requires: PagerDuty integration | Requires: PagerDuty integration | Requires: PagerDuty integration | Requires: PagerDuty integration | 🔴 BLOCKED: Investigate Prometheus deployment first | Requires: PagerDuty integration
Layer 5 | Observability Outcomes | Change Volume (count) | Low | N/A - tracked via change management | N/A - tracked via change management | N/A - tracked via change management | N/A - tracked via change management | N/A - tracked via change management | N/A - tracked via change management

## Jira Backlog
TECH PLATFORM OBSERVABILITY - JIRA BACKLOG
Jira ID | Existing Jira | Summary | Priority | Size | Service(s) | Sprint Target | Status | Blocked By | Metrics Addressed | Notes
TP-001 |  | Investigate CMP-Adapter Prometheus deployment | Critical | M | CMP-Adapter | Sprint 1 | To Do |  | All CMP-Adapter metrics | BLOCKER: Must be resolved before any CMP-Adapter observability work
TP-002 |  | Add http_status label to Payroll metrics | Critical | S | Payroll | Sprint 1 | To Do |  | 5xx/4xx Errors, App Error Rate, Success Rate | Required for error rate calculations
TP-003 |  | Add histogram buckets to Gateway for P95/P99 latency | Critical | M | Gateway | Sprint 1 | To Do |  | HTTP Response Latency, Latency Metrics | Currently using estimated P95 (avg*2)
TP-004 | PS-721616 | Add endpoint/uri labels to Config-Mgr metrics | Critical | S | Config-Mgr | Sprint 1 | To Do |  | HTTP Response Latency, Latency Metrics | Enables per-endpoint latency analysis
TP-005 | PS-721616 | Add endpoint/uri labels to Model-Feedback metrics | Critical | S | Model-Feedback | Sprint 1 | To Do |  | HTTP Response Latency, Latency Metrics | Enables per-endpoint latency analysis
TP-006 |  | Build Grafana dashboard for Config-Mgr | Critical | L | Config-Mgr | Sprint 1-2 | To Do | TP-004 | 5xx/4xx Errors, Latency, Throughput, Success Rate | Core observability dashboard
TP-007 |  | Build Grafana dashboard for Model-Feedback | Critical | L | Model-Feedback | Sprint 1-2 | To Do | TP-005 | 5xx/4xx Errors, Latency, Throughput, Success Rate | Core observability dashboard
TP-008 |  | Build Grafana dashboard for Payroll | Critical | L | Payroll | Sprint 1-2 | To Do | TP-002 | 5xx/4xx Errors, Latency, Throughput, Success Rate | Core observability dashboard
TP-009 |  | Implement synthetic monitoring solution (internal) | Critical | XL | All Services | Sprint 2 | To Do |  | Actual Uptime | TBD - internal solution, no Datadog
TP-010 |  | Enhance Gateway dashboard with missing panels | High | M | Gateway | Sprint 2 | To Do |  | App Dependency Health, Custom Errors, Integration Metrics | Add dependency health, custom error monitoring
TP-011 |  | Enhance LLM dashboard with missing panels | High | M | LLM | Sprint 2 | To Do |  | App Dependency Health, Custom Errors, Integration Metrics | Add dependency health, custom error monitoring
TP-012 | PS-721596 | Investigate tenant metrics approach (substream_id) | High | M | All Services | Sprint 2 | To Do |  | Tenant Fairness, Tenant Error Rate, Tenant Latency | product_id not available; evaluate substream_id usage
TP-013 |  | Create tenant-level dashboard views | High | L | Gateway, LLM, Config-Mgr, Model-Feedback, Payroll | Sprint 2-3 | To Do | TP-012 | Tenant Fairness, Tenant Error Rate, Tenant Latency | Pending tenant metrics investigation
TP-014 |  | Complete LLM alert rules | High | S | LLM | Sprint 2 | To Do |  | Alerts Configured w/ Actionable SOPs | Partial alerts exist
TP-015 |  | Create alert rules for Config-Mgr | High | M | Config-Mgr | Sprint 2-3 | To Do | TP-006 | Alerts Configured w/ Actionable SOPs | Requires dashboard first
TP-016 |  | Create alert rules for Model-Feedback | High | M | Model-Feedback | Sprint 2-3 | To Do | TP-007 | Alerts Configured w/ Actionable SOPs | Requires dashboard first
TP-017 |  | Create alert rules for Payroll | High | M | Payroll | Sprint 3 | To Do | TP-002, TP-008 | Alerts Configured w/ Actionable SOPs | Blocked by http_status label
TP-018 |  | Complete LLM runbook/SOP documentation | High | S | LLM | Sprint 2 | To Do |  | MTTA, MTTM | Partial runbooks exist
TP-019 |  | Write runbook/SOP documentation for Config-Mgr | High | M | Config-Mgr | Sprint 3 | To Do | TP-015 | MTTA, MTTM | Requires alert rules first
TP-020 |  | Write runbook/SOP documentation for Model-Feedback | High | M | Model-Feedback | Sprint 3 | To Do | TP-016 | MTTA, MTTM | Requires alert rules first
TP-021 |  | Write runbook/SOP documentation for Payroll | High | M | Payroll | Sprint 3-4 | To Do | TP-017 | MTTA, MTTM | Requires alert rules first
TP-022 |  | Configure PagerDuty integration | High | L | All Services | Sprint 3 | To Do |  | Alerts Integration w/ PD, MTTA, MTTM, Incident Volume | Platform-wide integration
TP-023 |  | Configure ui-metadata.json for Mission Control | Medium | M | All Services | Sprint 4 | To Do |  | Mission Control: Service View Onboarded | Onboard all services to Mission Control
TP-024 |  | Configure health-metadata.json for Gateway | Medium | S | Gateway | Sprint 4 | To Do |  | MC: Critical Health, Dependencies, Cloud Infra | Mission Control health integration
TP-025 |  | Configure health-metadata.json for LLM | Medium | S | LLM | Sprint 4 | To Do |  | MC: Critical Health, Dependencies, Cloud Infra | Mission Control health integration
TP-026 |  | Configure health-metadata.json for Config-Mgr | Medium | S | Config-Mgr | Sprint 4 | To Do |  | MC: Critical Health, Dependencies, Cloud Infra | Mission Control health integration
TP-027 |  | Configure health-metadata.json for Model-Feedback | Medium | S | Model-Feedback | Sprint 4 | To Do |  | MC: Critical Health, Dependencies, Cloud Infra | Mission Control health integration
TP-028 |  | Configure health-metadata.json for Payroll | Medium | S | Payroll | Sprint 4 | To Do |  | MC: Critical Health, Dependencies, Cloud Infra | Mission Control health integration
TP-029 | PS-721646 | Configure Arize Dashboard for Token/Cost Metrics | Medium | M | LLM | Sprint 4 | To Do |  | Usage Metrics, Adoption Metrics | LLM-specific usage tracking
SUMMARY
Total Jiras: |  | 29
Critical: |  | 9
High: |  | 13
Medium: |  | 7
SIZE LEGEND
S = Small |  | 1-2 days
M = Medium |  | 3-5 days
L = Large |  | 1-2 weeks
XL = Extra Large |  | 2+ weeks