## Prioritized Tasks
Rank | Phase | Priority | Service | Lang | Metric | Status | Work Required | Effort | Epic
1 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | open-telemetry-collector | Go | 5xx Errors Trend | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
2 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | open-telemetry-collector | Go | HTTP Response Latency | Not Implemented | BLOCKED: No latency metrics - needs instrumentation | S | Observability Dashboard Buildout
3 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | open-telemetry-collector | Go | App Error Rate | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
4 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | open-telemetry-collector | Go | Success Rate | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
5 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | open-telemetry-collector | Go | Latency Metrics | Not Implemented | BLOCKED: No latency metrics - needs instrumentation | S | Observability Dashboard Buildout
6 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | cmp-adapter | Java | 5xx Errors Trend | Not Implemented | BLOCKED: Service not found in Prometheus | S | Observability Dashboard Buildout
7 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | cmp-adapter | Java | HTTP Response Latency | Not Implemented | BLOCKED: Service not found | S | Observability Dashboard Buildout
8 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | cmp-adapter | Java | App Error Rate | Not Implemented | BLOCKED: Service not found in Prometheus | S | Observability Dashboard Buildout
9 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | cmp-adapter | Java | Success Rate | Not Implemented | BLOCKED: Service not found in Prometheus | S | Observability Dashboard Buildout
10 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | cmp-adapter | Java | Latency Metrics | Not Implemented | BLOCKED: Service not found | S | Observability Dashboard Buildout
11 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | config-manager | Python | 5xx Errors Trend | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
12 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | config-manager | Python | HTTP Response Latency | Implemented | VALIDATED: Histogram buckets available | S | Observability Dashboard Buildout
13 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | config-manager | Python | App Error Rate | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
14 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | config-manager | Python | Success Rate | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
15 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | config-manager | Python | Latency Metrics | Implemented | VALIDATED: Histogram buckets available | S | Observability Dashboard Buildout
16 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | model-feedback | Python | 5xx Errors Trend | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
17 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | model-feedback | Python | HTTP Response Latency | Implemented | VALIDATED: Histogram buckets available | S | Observability Dashboard Buildout
18 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | model-feedback | Python | App Error Rate | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
19 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | model-feedback | Python | Success Rate | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
20 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | model-feedback | Python | Latency Metrics | Implemented | VALIDATED: Histogram buckets available | S | Observability Dashboard Buildout
21 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | otel-event-processor | Python | 5xx Errors Trend | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
22 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | otel-event-processor | Python | HTTP Response Latency | Not Implemented | BLOCKED: No latency metrics - needs instrumentation | S | Observability Dashboard Buildout
23 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | otel-event-processor | Python | App Error Rate | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
24 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | otel-event-processor | Python | Success Rate | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
25 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | otel-event-processor | Python | Latency Metrics | Not Implemented | BLOCKED: No latency metrics - needs instrumentation | S | Observability Dashboard Buildout
26 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | open-telemetry-collector | Go | Alerts Integration w/ PD | Not Implemented | Create alert rules with SOPs and PD integration | S | Alerting & Incident Response
27 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | datascience-gateway | Java | Success Rate | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Instrumentation
28 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | open-telemetry-collector | Go | Alerts Configured w/ Actionable SOPs | Not Implemented | Create alert rules with SOPs and PD integration | M | Alerting & Incident Response
29 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | cmp-adapter | Java | Alerts Integration w/ PD | Not Implemented | Create alert rules with SOPs and PD integration | S | Alerting & Incident Response
30 | Phase 1: Quick Wins (Weeks 1-4) | P1 - Critical | config-manager | Python | Alerts Integration w/ PD | Not Implemented | Create alert rules with SOPs and PD integration | S | Alerting & Incident Response
31 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | model-feedback | Python | Alerts Integration w/ PD | Not Implemented | Create alert rules with SOPs and PD integration | S | Alerting & Incident Response
32 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | otel-event-processor | Python | Alerts Integration w/ PD | Not Implemented | Create alert rules with SOPs and PD integration | S | Alerting & Incident Response
33 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | open-telemetry-collector | Go | Critical Business Metrics | Not Implemented | Instrument custom business metrics | M | Business Metrics Instrumentation
34 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | open-telemetry-collector | Go | App Dependency Health Checks | Not Implemented | No dependency health checks | M | Observability Instrumentation
35 | Phase 2: Alerting (Weeks 3-6) | P2 - High | open-telemetry-collector | Go | 4xx Errors Trend | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
36 | Phase 2: Alerting (Weeks 3-6) | P2 - High | open-telemetry-collector | Go | Throughput Metrics | Not Implemented | BLOCKED: No HTTP metrics | S | Observability Dashboard Buildout
37 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | cmp-adapter | Java | Alerts Configured w/ Actionable SOPs | Not Implemented | Create alert rules with SOPs and PD integration | M | Alerting & Incident Response
38 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | config-manager | Python | Alerts Configured w/ Actionable SOPs | Not Implemented | Create alert rules with SOPs and PD integration | M | Alerting & Incident Response
39 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | model-feedback | Python | Alerts Configured w/ Actionable SOPs | Not Implemented | Create alert rules with SOPs and PD integration | M | Alerting & Incident Response
40 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | otel-event-processor | Python | Alerts Configured w/ Actionable SOPs | Not Implemented | Create alert rules with SOPs and PD integration | M | Alerting & Incident Response
41 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | cmp-adapter | Java | Critical Business Metrics | Not Implemented | Instrument custom business metrics | M | Business Metrics Instrumentation
42 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | config-manager | Python | Critical Business Metrics | Not Implemented | Instrument custom business metrics | M | Business Metrics Instrumentation
43 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | model-feedback | Python | Critical Business Metrics | Not Implemented | Instrument custom business metrics | M | Business Metrics Instrumentation
44 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | otel-event-processor | Python | Critical Business Metrics | Not Implemented | Instrument custom business metrics | M | Business Metrics Instrumentation
45 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | cmp-adapter | Java | App Dependency Health Checks | Not Implemented | No dependency health checks | M | Observability Instrumentation
46 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | config-manager | Python | App Dependency Health Checks | Not Implemented | No dependency health checks | M | Observability Instrumentation
47 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | model-feedback | Python | App Dependency Health Checks | Not Implemented | No dependency health checks | M | Observability Instrumentation
48 | Phase 2: Alerting (Weeks 3-6) | P1 - Critical | otel-event-processor | Python | App Dependency Health Checks | Not Implemented | No dependency health checks | M | Observability Instrumentation
49 | Phase 2: Alerting (Weeks 3-6) | P2 - High | cmp-adapter | Java | 4xx Errors Trend | Not Implemented | BLOCKED: Service not found in Prometheus | S | Observability Dashboard Buildout
50 | Phase 2: Alerting (Weeks 3-6) | P2 - High | cmp-adapter | Java | App (Custom) Errors Monitoring | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
51 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | cmp-adapter | Java | Throughput Metrics | Not Implemented | BLOCKED: No HTTP metrics | S | Observability Dashboard Buildout
52 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | config-manager | Python | 4xx Errors Trend | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
53 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | config-manager | Python | Throughput Metrics | Implemented | VALIDATED: rate(http_request_count_total) available | S | Observability Dashboard Buildout
54 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | model-feedback | Python | 4xx Errors Trend | Implemented | VALIDATED: Metrics available - create dashboard | S | Observability Dashboard Buildout
55 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | model-feedback | Python | Throughput Metrics | Implemented | VALIDATED: rate(http_request_count_total) available | S | Observability Dashboard Buildout
56 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | otel-event-processor | Python | 4xx Errors Trend | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | S | Observability Dashboard Buildout
57 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | otel-event-processor | Python | Throughput Metrics | Not Implemented | BLOCKED: No HTTP metrics | S | Observability Dashboard Buildout
58 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | llm-service | Python | Critical Business Metrics | Partial | Instrument custom business metrics | L | Business Metrics Instrumentation
59 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | datascience-gateway | Java | Critical Business Metrics | Not Implemented | Instrument custom business metrics | M | Business Metrics Instrumentation
60 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | open-telemetry-collector | Go | Actual Uptime | Not Implemented | Implement synthetic monitoring tests | L | Synthetic Monitoring Implementation
61 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | datascience-gateway | Java | App Dependency Health Checks | Not Implemented | No dependency health checks | M | Observability Instrumentation
62 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | llm-service | Python | App Dependency Health Checks | Not Implemented | No dependency health checks in dashboard | M | Observability Instrumentation
63 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | datascience-gateway | Java | App (Custom) Errors Monitoring | Partial | JVM memory alert exists | S | Observability Instrumentation
64 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | cmp-adapter | Java | Actual Uptime | Not Implemented | Implement synthetic monitoring tests | L | Synthetic Monitoring Implementation
65 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | config-manager | Python | Actual Uptime | Not Implemented | Implement synthetic monitoring tests | L | Synthetic Monitoring Implementation
66 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | model-feedback | Python | Actual Uptime | Not Implemented | Implement synthetic monitoring tests | L | Synthetic Monitoring Implementation
67 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | otel-event-processor | Python | Actual Uptime | Not Implemented | Implement synthetic monitoring tests | L | Synthetic Monitoring Implementation
68 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | datascience-gateway | Java | Actual Uptime | Not Implemented | Implement synthetic monitoring tests | L | Synthetic Monitoring Implementation
69 | Phase 3: Dashboards (Weeks 5-10) | P1 - Critical | llm-service | Python | Actual Uptime | Not Implemented | Implement synthetic monitoring tests | L | Synthetic Monitoring Implementation
70 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | open-telemetry-collector | Go | App (Custom) Errors Monitoring | Not Implemented | No custom error monitoring | M | Observability Instrumentation
71 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | open-telemetry-collector | Go | Integration Metrics | Not Implemented | No integration metrics | M | Observability Instrumentation
72 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | llm-service | Python | Tenant: Response Latency | Implemented | VALIDATED: Histogram buckets available | M | Tenant Observability Instrumentation
73 | Phase 3: Dashboards (Weeks 5-10) | P3 - Medium | open-telemetry-collector | Go | Usage Metrics | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
74 | Phase 3: Dashboards (Weeks 5-10) | P3 - Medium | open-telemetry-collector | Go | Historical Trends | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
75 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | cmp-adapter | Java | Integration Metrics | Not Implemented | No integration metrics | M | Observability Instrumentation
76 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | config-manager | Python | App (Custom) Errors Monitoring | Not Implemented | No custom error monitoring | M | Observability Instrumentation
77 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | config-manager | Python | Integration Metrics | Not Implemented | No integration metrics | M | Observability Instrumentation
78 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | model-feedback | Python | App (Custom) Errors Monitoring | Not Implemented | No custom error monitoring | M | Observability Instrumentation
79 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | model-feedback | Python | Integration Metrics | Not Implemented | No integration metrics | M | Observability Instrumentation
80 | Phase 3: Dashboards (Weeks 5-10) | P2 - High | otel-event-processor | Python | App (Custom) Errors Monitoring | Not Implemented | No custom error monitoring | M | Observability Instrumentation
81 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | otel-event-processor | Python | Integration Metrics | Not Implemented | No integration metrics | M | Observability Instrumentation
82 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | cmp-adapter | Java | Usage Metrics | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
83 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | cmp-adapter | Java | Historical Trends | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
84 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | config-manager | Python | Usage Metrics | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
85 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | config-manager | Python | Historical Trends | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
86 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | model-feedback | Python | Usage Metrics | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
87 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | model-feedback | Python | Historical Trends | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
88 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | otel-event-processor | Python | Usage Metrics | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
89 | Phase 4: Instrumentation (Weeks 8-16) | P3 - Medium | otel-event-processor | Python | Historical Trends | Likely Available | Create dashboard panels and/or alert rules (metrics likely exist) | S | Observability Dashboard Buildout
90 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | open-telemetry-collector | Go | Tenant Fairness Checks | Not Implemented | BLOCKED: No metrics | L | Tenant Observability Instrumentation
91 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | open-telemetry-collector | Go | Tenant: Error Rate | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | L | Tenant Observability Instrumentation
92 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | open-telemetry-collector | Go | Tenant: Response Latency | Not Implemented | BLOCKED: No latency metrics - needs instrumentation | L | Tenant Observability Instrumentation
93 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | datascience-gateway | Java | Integration Metrics | Not Implemented | No integration metrics | M | Observability Instrumentation
94 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | datascience-gateway | Java | Throughput Metrics | Implemented | VALIDATED: rate(http_request_count_total) available | M | Observability Instrumentation
95 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | llm-service | Python | App (Custom) Errors Monitoring | Not Implemented | No custom error monitoring | M | Observability Instrumentation
96 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | llm-service | Python | Integration Metrics | Not Implemented | No integration health metrics | M | Observability Instrumentation
97 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | cmp-adapter | Java | Tenant Fairness Checks | Not Implemented | Add product_id label to metrics instrumentation | L | Tenant Observability Instrumentation
98 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | cmp-adapter | Java | Tenant: Error Rate | Not Implemented | BLOCKED: Service not found in Prometheus | L | Tenant Observability Instrumentation
99 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | cmp-adapter | Java | Tenant: Response Latency | Not Implemented | BLOCKED: Service not found | L | Tenant Observability Instrumentation
100 | Phase 4: Instrumentation (Weeks 8-16) | P2 - High | config-manager | Python | Tenant Fairness Checks | Partial | VALIDATED: substream_id available (product_id missing) | L | Tenant Observability Instrumentation
101 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | config-manager | Python | Tenant: Error Rate | Implemented | VALIDATED: Metrics available - create dashboard | L | Tenant Observability Instrumentation
102 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | config-manager | Python | Tenant: Response Latency | Implemented | VALIDATED: Histogram buckets available | L | Tenant Observability Instrumentation
103 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | model-feedback | Python | Tenant Fairness Checks | Partial | VALIDATED: substream_id available (product_id missing) | L | Tenant Observability Instrumentation
104 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | model-feedback | Python | Tenant: Error Rate | Implemented | VALIDATED: Metrics available - create dashboard | L | Tenant Observability Instrumentation
105 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | model-feedback | Python | Tenant: Response Latency | Implemented | VALIDATED: Histogram buckets available | L | Tenant Observability Instrumentation
106 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | otel-event-processor | Python | Tenant Fairness Checks | Not Implemented | BLOCKED: No metrics | L | Tenant Observability Instrumentation
107 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | otel-event-processor | Python | Tenant: Error Rate | Not Implemented | BLOCKED: No HTTP metrics - needs instrumentation | L | Tenant Observability Instrumentation
108 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | otel-event-processor | Python | Tenant: Response Latency | Not Implemented | BLOCKED: No latency metrics - needs instrumentation | L | Tenant Observability Instrumentation
109 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | datascience-gateway | Java | Tenant Fairness Checks | Partial | VALIDATED: substream_id available (product_id missing) | L | Tenant Observability Instrumentation
110 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | datascience-gateway | Java | Tenant: Error Rate | Implemented | VALIDATED: Metrics available - create dashboard | L | Tenant Observability Instrumentation
111 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | datascience-gateway | Java | Tenant: Response Latency | Partial | VALIDATED: Use avg*2 estimation (no histogram buckets) | L | Tenant Observability Instrumentation
112 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | llm-service | Python | Tenant Fairness Checks | Partial | VALIDATED: substream_id available (product_id missing) | L | Tenant Observability Instrumentation
113 | Phase 5: Tenant & Advanced (Weeks 12-20) | P2 - High | llm-service | Python | Tenant: Error Rate | Implemented | VALIDATED: Metrics available - create dashboard | L | Tenant Observability Instrumentation
114 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | open-telemetry-collector | Go | Adoption Metrics | Not Implemented | No adoption tracking | M | Observability Instrumentation
115 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | cmp-adapter | Java | Adoption Metrics | Not Implemented | No adoption tracking | M | Observability Instrumentation
116 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | config-manager | Python | Adoption Metrics | Not Implemented | No adoption tracking | M | Observability Instrumentation
117 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | model-feedback | Python | Adoption Metrics | Not Implemented | No adoption tracking | M | Observability Instrumentation
118 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | otel-event-processor | Python | Adoption Metrics | Not Implemented | No adoption tracking | M | Observability Instrumentation
119 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | datascience-gateway | Java | Usage Metrics | Not Implemented | No usage dashboard | M | Observability Instrumentation
120 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | datascience-gateway | Java | Adoption Metrics | Not Implemented | No adoption tracking | M | Observability Instrumentation
121 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | datascience-gateway | Java | Historical Trends | Not Implemented | Alerts only, no trend dashboard | M | Observability Instrumentation
122 | Phase 5: Tenant & Advanced (Weeks 12-20) | P3 - Medium | llm-service | Python | Adoption Metrics | Not Implemented | No adoption tracking | M | Observability Instrumentation

## Phase Summary
Phase | Total Tasks | P1 Tasks | P2 Tasks | P3 Tasks | Small (S) | Medium (M) | Large (L) | Est. Days
Phase 1: Quick Wins (Weeks 1-4) | 30 | 30 | 0 | 0 | 29 | 1 | 0 | 47.5
Phase 2: Alerting (Weeks 3-6) | 20 | 16 | 4 | 0 | 6 | 14 | 0 | 65
Phase 3: Dashboards (Weeks 5-10) | 30 | 11 | 17 | 2 | 10 | 12 | 8 | 143
Phase 4: Instrumentation (Weeks 8-16) | 20 | 0 | 12 | 8 | 8 | 5 | 7 | 102
Phase 5: Tenant & Advanced (Weeks 12-20) | 22 | 0 | 13 | 9 | 0 | 9 | 13 | 166

## Service Priority
Service | Language | Total Tasks | Quick Wins | P1 Tasks | Est. Days | Recommended Start
open-telemetry-collector | Go | 20 | 9 | 10 | 79 | Sprint 3+
cmp-adapter | Java | 20 | 10 | 10 | 76.5 | Investigate
config-manager | Python | 20 | 9 | 10 | 79 | Sprint 1
model-feedback | Python | 20 | 9 | 10 | 79 | Sprint 1
otel-event-processor | Python | 20 | 9 | 10 | 79 | Sprint 3+
datascience-gateway | Java | 13 | 0 | 4 | 71 | Dashboard Only
llm-service | Python | 9 | 0 | 3 | 60 | Done

## Metric Validation
Service | Language | Metric | Query | Series | Status | Notes
config-manager | Python | HTTP Counts | http_request_count_total{name="service-config-manager"} | 1,440 | READY | Dashboard ready
config-manager | Python | Latency Buckets | request_incoming_duration_seconds_bucket{...} | 75 | READY | P50/P95/P99 ready
config-manager | Python | Tenant (substream_id) | http_request_count_total{..., substream_id!=""} | 1,452 | READY | Tenant metrics ready
model-feedback | Python | HTTP Counts | http_request_count_total{name="service-model-feedback"} | 7 | READY | Dashboard ready
model-feedback | Python | Latency Buckets | request_incoming_duration_seconds_bucket{...} | 120 | READY | P50/P95/P99 ready
model-feedback | Python | Tenant (substream_id) | http_request_count_total{..., substream_id!=""} | 7 | READY | Tenant metrics ready
datascience-gateway | Java | HTTP Counts | http_server_requests_seconds_count{application="gateway"} | 1,032 | READY | Dashboard ready
datascience-gateway | Java | Latency Sum | http_server_requests_seconds_sum{application="gateway"} | 998 | PARTIAL | Use avg*2 (no buckets)
datascience-gateway | Java | Latency Buckets | http_server_requests_seconds_bucket{...} | 0 | GAP | NO HISTOGRAM BUCKETS
datascience-gateway | Java | JVM Memory | jvm_memory_used_bytes{application="gateway"} | 96 | READY | JVM alerting ready
datascience-gateway | Java | Tenant (substream_id) | http_server_requests_seconds_count{..., substream_id!=""} | 998 | READY | Tenant metrics ready
datascience-gateway | Java | Alerts + Runbook | N/A | N/A | DONE | EXISTS in ds-gateway-alerting-rules.yaml
llm-service | Python | All Metrics | See ds-llm-passthrough-api-observability.json | N/A | DONE | HAS FULL DASHBOARD
llm-service | Python | Tenant (substream_id) | http_request_count_total{..., substream_id!=""} | 89 | READY | In dashboard
llm-service | Python | Container Metrics | container_cpu/memory_* | 28+28 | READY | In dashboard
llm-service | Python | Alerts + Runbook | N/A | N/A | DONE | EXISTS in ds-llm-alert-rules.yaml
open-telemetry-collector | Go | HTTP Counts | http_request_count_total{name="service-open-telemetry-collector"} | 0 | MISSING | NEEDS INSTRUMENTATION
otel-event-processor | Python | HTTP Counts | http_request_count_total{name="service-otel-event-processor"} | 0 | MISSING | NEEDS INSTRUMENTATION
cmp-adapter | Java | All Metrics | http_server_requests_seconds_count{application=~".*cmp.*"} | 0 | NOT FOUND | Check deployment/labels
KEY FINDINGS (25 Queries Validated):
✅ READY FOR DASHBOARDS: config-manager, model-feedback, datascience-gateway
✅ ALREADY COMPLETE: llm-service (dashboard), gateway + llm (alerts/runbooks)
⚠️ PARTIAL: Gateway latency (use avg*2), Tenant metrics (use substream_id)
❌ BLOCKED: otel-collector, otel-event-processor (need instrumentation)
❌ NOT FOUND: cmp-adapter (check deployment)
RUNBOOKS/SOPs STATUS:
• datascience-gateway: ✅ EXISTS at engconf.int.kronos.com/spaces/AI/pages/gateway-runbook
• llm-service: ✅ EXISTS at engconf.int.kronos.com/spaces/AI/pages/llm-runbook
• config-manager: ❌ NEEDS CREATION
• model-feedback: ❌ NEEDS CREATION

## Priority Definitions
Priority | Label | Definition | Response Time | Examples
P1 | Critical | Directly impacts incident detection, customer experience, or production reliability | Current Sprint | 5xx errors, latency alerting, uptime
P2 | High | Enables proactive monitoring, resource optimization, or compliance | Next 2 Sprints | 4xx errors, tenant metrics, throughput
P3 | Medium | Provides business insights, trend analysis, or enhanced troubleshooting | 1-2 Quarters | Usage metrics, adoption, historical trends