## Executive Summary
Tech Platform Observability Initiative - Executive Summary
METRIC PRIORITIES SUMMARY
Priority | Count | Focus Areas | Response Time | Sprint Target
Critical | 7 | Error rates, latency, uptime, success rate | Immediate (<5 min) | Sprint 1-2
High | 13 | Tenant metrics, throughput, alerts, dependencies | Within 1 hour | Sprint 2-4
Medium | 8 | Usage, adoption, historical trends, Mission Control | 24-48 hours | Sprint 4-6
Low | 2 | Incident/change volume reporting | Weekly review | Backlog
SERVICE READINESS STATUS
Service | Language | Prometheus Status | Alerts/Runbooks | Recommended Action
service-config-manager | Python | ✅ Ready | ❌ Needs creation | Build dashboards → Create alerts
service-model-feedback | Python | ✅ Ready | ❌ Needs creation | Build dashboards → Create alerts
service-datascience-gateway | Java | ⚠️ Partial (no histogram) | ✅ Exists | Dashboard exists - enhance
service-large-language-model | Python | ✅ Ready | ✅ Exists | Complete - minor enhancements
service-open-telemetry-collector | Go | ❌ Missing | ❌ Missing | BLOCKED - needs instrumentation
service-otel-event-processor | Python | ❌ Missing | ❌ Missing | BLOCKED - needs instrumentation
service-cmp-adapter | Java | ❌ Not Found | ❌ Missing | BLOCKED - investigate deployment
service-payroll-model | Python | ⚠️ Partial (no status label) | ❌ Needs creation | Has endpoint labels ✅ but no HTTP status - can't calculate error rates

## High-Level Tasks
HIGH-LEVEL TASKS & WORK STREAMS
Category | Task | Services Affected | Priority | Effort | Dependencies
Dashboard Construction | Build Grafana dashboards for Python services | service-config-manager, service-model-feedback, service-payroll-model | Critical | S (2-3 days) | Metrics validated ✅
Dashboard Construction | Enhance existing LLM service dashboard | service-large-language-model | High | S (1-2 days) | Dashboard exists ✅
Dashboard Construction | Enhance Gateway dashboard (add missing panels) | service-datascience-gateway | High | S (2 days) | Dashboard exists ✅
Dashboard Construction | Create tenant-level dashboard views | service-config-manager, service-model-feedback, service-datascience-gateway, service-large-language-model, service-payroll-model | High | M (1 week) | substream_id available
Alerting & SOPs | Create alert rules for Python services (needing alerts) | service-config-manager, service-model-feedback, service-payroll-model (service-large-language-model already has alerts; service-otel-event-processor BLOCKED) | Critical | M (3-4 days) | Dashboards first
Alerting & SOPs | Write runbook/SOP documentation | service-config-manager, service-model-feedback, service-payroll-model (service-large-language-model already has runbook) | Critical | M (3-4 days) | Alert rules first
Alerting & SOPs | Configure PagerDuty integration | service-datascience-gateway, service-large-language-model (existing alerts); service-config-manager, service-model-feedback, service-payroll-model (after alert creation) | Critical | S (1-2 days) | Alert rules exist
Service Instrumentation | Add HTTP metrics to service-open-telemetry-collector | service-open-telemetry-collector | Critical | M (1 week) | Code changes required
Service Instrumentation | Add HTTP metrics to service-otel-event-processor | service-otel-event-processor | Critical | M (1 week) | Code changes required
Service Instrumentation | Investigate service-cmp-adapter deployment | service-cmp-adapter | Critical | S (investigation) | Unknown - needs research
Service Instrumentation | Add histogram buckets to Gateway | service-datascience-gateway | High | M (3-5 days) | Java code changes
Service Instrumentation | Add product_id label for tenant metrics | All 8 services (architecture decision) | High | L (2+ weeks) | Architecture decision
Mission Control | Onboard services to Mission Control | All 8 services (config-based, not metric-dependent) | Medium | M (1 week) | ui-metadata.json config
Mission Control | Configure health-metadata.json | 5 services with metrics: service-config-manager, service-model-feedback, service-payroll-model, service-large-language-model, service-datascience-gateway | Medium | M (1 week) | Dashboards exist first
Synthetic Monitoring | Implement synthetic availability tests | All 8 services (external testing, not metric-dependent) | Critical | L (2+ weeks) | Datadog access
Service Instrumentation | Add HTTP status label to service-payroll-model metrics | service-payroll-model | High | M (3-5 days) | Different instrumentation library - has endpoint but no status

## Blockers & Issues
KNOWN BLOCKERS & ISSUES
Severity | Issue | Impact | Services Affected | Mitigation / Next Steps
🔴 Blocker | service-open-telemetry-collector has NO HTTP metrics | Cannot build dashboards or alerts for 5 critical metrics | service-open-telemetry-collector | Requires Go instrumentation - engage service team
🔴 Blocker | service-otel-event-processor has NO HTTP metrics | Cannot build dashboards or alerts for 5 critical metrics | service-otel-event-processor | Requires Python instrumentation - engage service team
🔴 Blocker | service-cmp-adapter not found in Prometheus | Cannot validate any metrics for this service | service-cmp-adapter | Investigate: deployment labels, namespace, scrape config
🟠 Issue | service-datascience-gateway missing histogram buckets | P95/P99 latency requires avg*2 estimation (inaccurate) | service-datascience-gateway | Add histogram instrumentation to Java service
🟠 Issue | product_id label missing across all services | True tenant-level metrics not possible | All services | Use substream_id as proxy; plan product_id instrumentation
🟠 Issue | No synthetic monitoring implemented | Actual Uptime metric cannot be measured | All services | Requires Datadog synthetic test setup
🟡 Risk | Runbooks missing for 2 services | Alerts without SOPs reduce incident response effectiveness | service-config-manager, service-model-feedback | Create runbooks after alert rules defined
🟠 Issue | Endpoint labels missing on Python latency metrics | Cannot identify slow endpoints for Python services - only aggregate latency. Gateway (Java) DOES have uri/method labels. | service-config-manager, service-model-feedback (confirmed missing) | Add endpoint/path label to Python request_incoming_duration_seconds instrumentation. Gateway is OK.
🟠 Issue | service-payroll-model missing HTTP status label | Cannot calculate 5xx/4xx error rates - request_count_total has endpoint/method but no status label | service-payroll-model | Different instrumentation library than other Python services; need to add status label or use log-based error tracking

## Unknowns & Questions
UNKNOWNS & OPEN QUESTIONS
Category | Question / Unknown | Why It Matters | Owner / Action
Architecture | Why is service-cmp-adapter not in Prometheus? | Cannot assess observability coverage without understanding deployment | Investigate deployment config, namespace, service mesh
Architecture | What is the service-cmp-adapter service purpose and criticality? | Need to prioritize instrumentation effort appropriately | Check with service team / architecture docs
Instrumentation | Can we add product_id label without breaking existing queries? | Tenant-level metrics depend on this; cardinality concerns | Discuss with platform team
Instrumentation | What histogram buckets are appropriate for Gateway latency? | Wrong buckets = inaccurate percentiles | Analyze current latency distribution
Tooling | Do we have Datadog access for synthetic monitoring? | Actual Uptime metric requires synthetic tests | Check with Ops / request access if needed
Tooling | Is Arize available for LLM token/cost tracking? | Usage Metrics, Critical Business Metrics depend on Arize | Confirm Arize access and integration status
Process | What is the SOP template/standard for runbooks? | Need consistent format across services | Get template from existing gateway/llm runbooks
Process | Who owns PagerDuty escalation policy setup? | Alerts need proper routing to on-call | Confirm with NOC / Ops team
Scope | Are there additional services beyond the 7 identified? | May be missing observability coverage | Validate service inventory with team
Instrumentation | What Python instrumentation library is used, and can it add endpoint labels? | Need to understand how to add endpoint/path labels to request_incoming_duration_seconds | Check Python service code for metrics library (prometheus_client? opentelemetry?)
New Service | [RESOLVED] service-service-payroll-model uses different instrumentation | Different library than other Python services: has endpoint/method labels ✅, but missing status label for error rates ❌ | Metrics: request_count_total (with endpoint), request_incoming/outgoing_duration_seconds
Instrumentation | Should Python services standardize on one instrumentation library? | service-payroll-model uses different library than service-config-manager/service-model-feedback - inconsistent metrics available | Evaluate: align on one approach or document differences for dashboard builders

## Recommended Roadmap
RECOMMENDED IMPLEMENTATION ROADMAP
Phase | Timing | Deliverables | Services | Success Criteria
Phase 1: Quick Wins | Weeks 1-2 | • Dashboards for service-config-manager, service-model-feedback, service-payroll-model • Enhance existing Gateway/LLM dashboards | service-config-manager, service-model-feedback, service-payroll-model, service-datascience-gateway, service-large-language-model (5 services with metrics) | 5 services with comprehensive dashboards
Phase 2: Alerting | Weeks 2-4 | • Alert rules for Python services • Runbook/SOP documentation • PagerDuty integration | service-config-manager, service-model-feedback, service-payroll-model (new alerts); service-datascience-gateway, service-large-language-model (enhance existing) | Alerts firing → PagerDuty → On-call for 5 services
Phase 3: Instrumentation | Weeks 4-8 | • HTTP metrics for service-open-telemetry-collector (Go) • HTTP metrics for service-otel-event-processor (Python) • Investigate service-cmp-adapter deployment • Add status label to service-payroll-model | service-open-telemetry-collector, service-otel-event-processor, service-cmp-adapter (blocked); service-payroll-model (status label gap) | 3 blocked services unblocked; service-payroll-model error rates enabled
Phase 4: Tenant Metrics | Weeks 6-10 | • Tenant dashboards using substream_id • Plan product_id instrumentation • Add endpoint labels to Python services | service-config-manager, service-model-feedback, service-payroll-model, service-datascience-gateway, service-large-language-model (substream_id ready) | Tenant-level visibility for error rate, latency across 5 services
Phase 5: Advanced | Weeks 10-16 | • Synthetic monitoring (Datadog) • Mission Control onboarding • Arize integration for LLM metrics | All 8 services (synthetics, Mission Control); service-large-language-model (Arize) | Actual Uptime measurable; Mission Control integration complete for all 8